## Activity
Date | Task/Activity | Primary Owner | Status | Expected Closure Date | Remark | Secondary Owner
2013-09-16 | To-Be process map review - Direct | Atik V |  |  |  | Soma | Sanjay B | Open
2013-09-16 | To-Be process map review - Indirect | Soma |  |  |  | Atik V | Gopi S | Closed
2013-09-16 | Indirect (iProcurement) Business Requirement review | Atik V |  |  |  | Gopi S | Atik V | Pending NBTY
2013-09-16 | Fit-Gap Analysis (Direct) | Madhur B |  |  |  | Gopi S | Deepak D
2013-09-16 | Approval Process - Direct | Deepak D |  |  |  | Atik V | Satyashree
2013-09-16 | Approval Process - Indirect | Deepak D |  |  |  | Atik V | Soma
2013-09-16 | Inventory Organization Analysis and future approach | Gopi S |  |  |  | Atik V | Madhur B
2013-09-16 | Automation Test Approach | Nishanth G |  |  |  | Madhur B | Shyam B
2013-09-16 | Supplier Hub Enhancements – High Priority (Analysis and Solution) | Satyashree |  |  |  | Deepak D | Srini G
2013-09-16 | Feasibility of Meta Data (Attachment) conversion for Contract Purchase Order and Blanket Purchase Agreement | Shyam B |  |  |  | Satyashree | Nishanth G
2013-09-16 | Key Product data for procurement process (Quality/Purchase specification & Item price default in PO) | Gopi S |  |  |  | Atik V | Ankit/Parul
2013-09-16 | E Biz Tax Demo | Deepak D |  |  |  | Ankit/Parul
2013-09-16 | Development Instance readiness and access to start critical patching or fixing Application bugs | Srini G |  |  |  | Deepak D
2013-09-16 | Offshore Infrastructure Issues | Shyam B |  |  |  | Deepak D
2013-09-16 | Finalize Project Plan for E Biz Tax, iSupplier & BI | Sanjay B